## Sheet1
HAL - Change Control Journal
Journal Identifier: Region letter & unique journal code: |  |  |  | 9 | Note: Each system will use its own journal. Use one row for each change.
System Identifier: Server name, services hosted, and IP Address: |  |  |  | Fedora-Mail-172.20.241.40
Date and time log was started: |  |  |  | 2019-02-23 15:00
Date and time log was completed:
Log Number | Line Number | Change Request Number | Change Type | Change Summary | Change Details | Impact / Outcome
This is a unique ID for this log within the HAL region, to enable merging and sorting. | Unique line number for each change item, to enable merging and sorting. | For example CCN-12-E-1001 | Routine or Emergency | Provide a brief summary of the change not to exceed 75 words. | Provide a complete explanation of the change. If this as for a routine change this duplicates the information on the change request form in every particular. It must include the roll back planning that was done. If emergency change, justify use of emergency change process. BE CERTAIN to include specific dates and times of all notable events in the progression of this change item. | Fully explain the outcome of the change and the impact of the change on the business unit.
9 | 1 | CCN-9-E-1000 | Emergency | Disabled Sshd | 02/23/2019 15:00:23 I disabled the program openssh server which is in charge of allowing remote users to connect and manage the server. | Remote users will no longer be able to login and manage the server
9 | 2 | CCN-9-E-1001 | Emergency | Disabled Crond | 02/23/2019 15:00:23 I disabled the program crond which is in charge of running scheduled tasks. | Scheduled tasks malicious and no will not run
9 | 3 | CCN-9-E-1002 | Emergency | Added Firewall Rules | 02/23/2019 15:05:21 A firewall was added to prevent access to services that are not required and could be potentially be used to aid in a breach. | Unexpected traffic will not be allowed into the server.
9 | 4 | CCN-9-E-1003 | Emergency | Changed passwords | 02/23/2019 15:03:41 User account password has been modified in the previous password was comprised. | The previous account passwords will not work.
9 | 5 | CCN-9-E-1004 | Emergency | Deleted old ssh keys | 02/23/2019 15:10:28 Some of the old users had there ssh keys still on the system which would allow them to login without a password. These keys have been removed. | Old users will not be able to login with there ssh keys.
9 | 6 | CCN-9-E-1005
9 | 7 | CCN-9-E-1006
9 | 8 | CCN-9-E-1007
9 | 9 | CCN-9-E-1008
9 | 10 | CCN-9-E-1009
9 | 11 | CCN-9-E-1010